Prevention North

Region1 WV Substance Abuse Prevention Services Sub-Grantee Statement of Work 2024-2025

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Community-Based Process Level of Effort: 25% | Identify 1 Coordinator of WV Prevention Services in Each County |  |  |
|  | Submit 2024 Comprehensive County Substance Abuse Prevention Plan To Include: Statement of Need Population of Focus Organizational Experience (Staff and Volunteers) Community Needs Assessment Logic Model Action Plan Data Collection and Performance Measurement Sustainability |  |  |
|  | Participate in Coalition Capacity-Building Training & TA |  |  |
|  | Facilitate a Minimum of 1 Community Coalition Meeting/Event Each Month |  |  |
|  | Attend Region1 WVSABG Sub-Grantee Meetings Quarterly |  |  |
|  | Attend Region1 Data & Planning Team Meetings Quarterly |  |  |
|  | Attend Region1 Women’s Network Meetings |  |  |
|  | Attend Any BBH or Office of Drug Control Policy Meetings in Region1 |  |  |
|  | Complete Annual CADCA Coalition Survey |  |  |
|  | Collection of Attendance Demographic Data & Participant Feedback |  |  |
|  | Assist with the Community Readiness and Needs Assessment |  |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Education Level of Effort: 25% | Coordinate the Implementation for a Minimum of 1 Evidence-Based Prevention Education Curriculum in Each County |  |  |
|  | Coordinate a Minimum of 2 Strategic Prevention Framework (SPF) Trainings in Each County |  |  |
|  | Coordinate a Minimum of 2 “The Prevention Guide What Works and What Doesn’t” Trainings in Each County |  |  |
|  | Coordinate a Minimum of 2 Substance Abuse Prevention Skills Training (SAPST) in Each County |  |  |
|  | Coordinate a Minimum of 2 BBH Evidence-Based Clearinghouse Trainings in Each County |  |  |
|  | Coordinate a Minimum of 2 Addressing Stigma Trainings in Each County |  |  |
|  | Complete National CADCA Coalition Academy |  |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Environmental Level of Effort: 20% | Promote Region1 Rx Drug Drop Boxes & Participate in Rx Take-Back Events in County |  |  |
|  | Distribute Deterra Prescription Drug Disposal Bags in County |  |  |
|  | Coordinate & Implement Synar Compliance Inspections in County |  |  |
|  | Identify and Implement a Minimum of 1 Environmental Strategy Based on Community Needs Assessments in Each County |  |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Alternatives Level of Effort: 15% | Establish or Maintain a Minimum of 1 Youth Coalition in Each County |  |  |
|  | Identify and Coordinate a Minimum of 1 Positive Youth Alternative Activity in Each County |  |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Information Dissemination Level of Effort: 10% | Coordinate Region1 Positive Community Norms Media Campaign Development & Implement in Each County | National Prevention Wk |  |
|  | Promote Prevention 1st, Help 4 WV, Help & Hope WV and Stigma Free WV, Children’s Crisis and Referral line, Naloxone, and Mental Health First Aid Training, and the 988 Suicide and Crisis Lifeline at Community Meetings & a Minimum of 1 Community-Based Event |  |  |
|  | Promote participation by Schools in the West Virginia School Learning Environmental Survey |  |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| ID & Referral Level of Effort: 5% | Facilitate Referral to Services in Each County |  |  |

Submit County Activity Reporting Forms (to Include Associated Costs) And Financial Reporting Forms No Later Than the 5th Work Day of the Following Month